## UI Validation
Page Name | UI Element | Expected Function | Test ID | Pass/Fail
index | "Log in" button | Go to login page | ui.1 | Pass
login | "Log in" button | Logs in, proceeds to home page | ui.2 | Fail
home | "Join" button | Goes to join page | ui.3 | Fail
home | "Host" button | Goes to host page | ui.4 | Fail
home | menu button | Opens side bar | ui.5 | Fail
home(side bar) | "Home" | Goes to home page | ui.6 | Pass
home (side bar) | "Session info" | Goes to info page | ui.7 | Pass
home (side bar) | "Spotify" | Goes to spotify page | ui.8 | Pass
home (side bar) | "YouTube" | Goes to youtube page | ui.9 | Pass
home (side bar) | "Log Out" | Logs out user, proceeds to index page | ui.10 | Fail
home (side bar) | x button | Closes side bar | ui.11 | Pass

## UI Remediation
TestID | Description | Severity (1 to 3) | Assigned | Completed
ui.2 | Temporary link to proceed to home page, but doesn't actually logs in user | 2 | Stephanie
ui.3 | Does not go to "join". Need to implement page | 1 | Stephanie
ui.4 | Does not go to "host". Need to implement page | 1 | Stephanie
ui.5 | Does open side bar, but when hovering over, it doesn't appear "clickable" | 1 | Stephanie
ui.10 | Temporary link to proceed to index page, but doesn't actually logs out user | 2 | Stephanie